## Sheet1
Project :-DREAM DELMONT_ G | Project :-DREAM DELMONT_ G | Project :-DREAM DELMONT_ G | Project :-DREAM DELMONT_ G | Project :-DREAM DELMONT_ G | Project :-DREAM DELMONT_ G | Project :-DREAM DELMONT_ G | Project :-DREAM DELMONT_ G | Project :-DREAM DELMONT_ G | Project :-DREAM DELMONT_ G | Project :-DREAM DELMONT_ G | Project :-DREAM DELMONT_ G | Project :-DREAM DELMONT_ G | Project :-DREAM DELMONT_ G | Project :-DREAM DELMONT_ G | Project :-DREAM DELMONT_ G | Project :-DREAM DELMONT_ G
Selected Group :- A1 WING | Selected Group :- A1 WING | Selected Group :- A1 WING | Selected Group :- A1 WING | Selected Group :- A1 WING | Selected Group :- A1 WING | Selected Group :- A1 WING | Selected Group :- A1 WING | Selected Group :- A1 WING | Selected Group :- A1 WING | Selected Group :- A1 WING | Selected Group :- A1 WING | Selected Group :- A1 WING | Selected Group :- A1 WING | Selected Group :- A1 WING | Selected Group :- A1 WING | Selected Group :- A1 WING
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 15597 | A1 WING |  | 0.0000 | 0.0000 | 0 | 15596 | 31 | 0 |  | Wing |  |  |  |  | 256989.0000
2 | 15599 | EXCAVATION WORK |  | 0.0000 | 0.0000 | 1 | 15597 | 31 | 0 |  | Wing |  |  |  |  | 256989.0000
3 | 15602 | DEWATERING WORK |  | 0.0000 | 0.0000 | 2 | 15599 | 31 | 0 |  | Wing |  |  |  |  | 256989.0000
4 | 15603 | ROCK ANCHORING |  | 0.0000 | 0.0000 | 2 | 15599 | 31 | 0 | [6 empty] | 256989.0000
5 | 15600 | RCC WORK |  | 0.0000 | 0.0000 | 1 | 15597 | 31 | 0 |  | Wing |  |  |  |  | 256989.0000
6 | 15623 | SUB- STRUCTURE |  | 0.0000 | 0.0000 | 5 | 15600 | 31 | 0 |  | Wing |  |  |  |  | 256989.0000
7 | 15625 | FOUNDATION WORK | SQF | 256989.0000 | 256989.0000 | 6 | 15623 | 4 | 3780 | FOUNDATION WORK | [5 empty] | 256989.0000
8 | 15626 | BASEMENT1 WORK | SQF | 256989.0000 | 256989.0000 | 6 | 15623 | 4 | 3781 | BASEMENT1 WORK | [5 empty] | 256989.0000
9 | 15627 | BASEMENT 2 WORK | SQF | 256989.0000 | 256989.0000 | 6 | 15623 | 4 | 3781 | BASEMENT1 WORK | [5 empty] | 256989.0000
10 | 15628 | BASEMENT 3 WORK | SQF | 256989.0000 | 256989.0000 | 6 | 15623 | 4 | 3781 | BASEMENT1 WORK | [5 empty] | 256989.0000
11 | 15624 | SUPER- STRUCTURE |  | 0.0000 | 0.0000 | 5 | 15600 | 31 | 0 |  | Wing |  |  |  |  | 256989.0000
12 | 15815 | 1ST FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3784 | 1ST FLOOR SLAB | [5 empty] | 131633.0000
13 | 15816 | 2ND FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3784 | 1ST FLOOR SLAB | [5 empty] | 131633.0000
14 | 15817 | 3RD FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
15 | 15818 | 4TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
16 | 15819 | 5TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
17 | 15820 | 6TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
18 | 15821 | 7TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
19 | 15822 | 8TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
20 | 15823 | 9TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
21 | 15824 | 10TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
22 | 15825 | 11TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
23 | 15826 | 12TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
24 | 15827 | 13TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
25 | 15828 | 14TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
26 | 15829 | 15TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
27 | 15830 | 16TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
28 | 15831 | 17TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
29 | 15832 | 18TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
30 | 15833 | 19TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
31 | 15834 | 20TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
32 | 15835 | 21ST FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
33 | 15836 | 22ND FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
34 | 15837 | 23RD FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
35 | 15838 | 24TH FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
36 | 15839 | TERRACE FLOOR SLAB | SQF | 5000.0000 | 131633.0000 | 11 | 15624 | 4 | 3785 | 2ND FLOOR SLAB | [5 empty] | 131633.0000
37 | 15601 | FINISHING WORK |  | 0.0000 | 0.0000 | 1 | 15597 | 31 | 0 |  | Wing |  |  |  |  | 256989.0000
38 | 15604 | GYPSUM WORK |  | 0.0000 | 0.0000 | 37 | 15601 | 31 | 0 |  | Wing |  |  |  |  | 256989.0000
39 | 15657 | 1ST FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3831 | 1ST FLOOR SLAB | [5 empty] | 256989.0000
40 | 15658 | 2ND FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3832 | 2ND FLOOR SLAB | [5 empty] | 256989.0000
41 | 15659 | 3RD FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3833 | 3RD FLOOR SLAB | [5 empty] | 256989.0000
42 | 15660 | 4TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3834 | 4TH FLOOR SLAB | [5 empty] | 256989.0000
43 | 15661 | 5TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3835 | 5TH FLOOR SLAB | [5 empty] | 256989.0000
44 | 15662 | 6TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3836 | 6TH FLOOR SLAB | [5 empty] | 256989.0000
45 | 15663 | 7TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
46 | 15664 | 8TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
47 | 15665 | 9TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
48 | 15666 | 10TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
49 | 15667 | 11TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
50 | 15668 | 12TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
51 | 15669 | 13TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
52 | 15670 | 14TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
53 | 15671 | 15TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
54 | 15672 | 16TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
55 | 15673 | 17TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
56 | 15674 | 18TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
57 | 15675 | 19TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
58 | 15676 | 20TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
59 | 15677 | 21TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
60 | 15678 | 22TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
61 | 15679 | 23TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
62 | 15680 | 24TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 38 | 15604 | 4 | 3837 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
63 | 15605 | MASONARY WORK |  | 0.0000 | 0.0000 | 37 | 15601 | 31 | 0 |  | Wing |  |  |  |  | 256989.0000
64 | 15681 | 1ST FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3799 | 1ST FLOOR SLAB | Wing |  |  |  |  | 256989.0000
65 | 15682 | 2ND FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3799 | 1ST FLOOR SLAB | [5 empty] | 256989.0000
66 | 15683 | 3RD FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3799 | 1ST FLOOR SLAB | [5 empty] | 256989.0000
67 | 15684 | 4TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3799 | 1ST FLOOR SLAB | [5 empty] | 256989.0000
68 | 15685 | 5TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3799 | 1ST FLOOR SLAB | [5 empty] | 256989.0000
69 | 15686 | 6TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3799 | 1ST FLOOR SLAB | [5 empty] | 256989.0000
70 | 15687 | 7TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3799 | 1ST FLOOR SLAB | [5 empty] | 256989.0000
71 | 15688 | 8TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3799 | 1ST FLOOR SLAB | [5 empty] | 256989.0000
72 | 15689 | 9TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3796 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
73 | 15690 | 10TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3796 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
74 | 15691 | 11TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3796 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
75 | 15692 | 12TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3796 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
76 | 15693 | 13TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3796 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
77 | 15694 | 14TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3796 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
78 | 15695 | 15TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3796 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
79 | 15696 | 16TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3796 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
80 | 15697 | 17TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3796 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
81 | 15698 | 18 TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3796 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
82 | 15699 | 19TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3796 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
83 | 15700 | 20TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3796 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
84 | 15701 | 21ST FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3796 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
85 | 15702 | 22ND FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3796 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
86 | 15703 | 23RD FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3796 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
87 | 15704 | 24TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3796 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
88 | 15705 | BASEMENT 1 | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3797 | BASEMENT 1 | [5 empty] | 256989.0000
89 | 15706 | BASEMENT 2 | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3797 | BASEMENT 1 | [5 empty] | 256989.0000
90 | 15707 | GROUND FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3798 | GROUND FLOOR SLAB | [5 empty] | 256989.0000
91 | 15708 | TERRACE FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3805 | TERRACE FLOOR SLAB | [5 empty] | 256989.0000
92 | 15709 | OHWT/ LMR SLAB | SQF | 131633.0000 | 131633.0000 | 63 | 15605 | 4 | 3804 | OHWT/ LMR SLAB | [5 empty] | 256989.0000
93 | 15606 | PLASTER WORK |  | 0.0000 | 0.0000 | 37 | 15601 | 31 | 0 |  | Wing |  |  |  |  | 256989.0000
94 | 15710 | INTERNAL PLASTER WORK |  | 0.0000 | 0.0000 | 93 | 15606 | 31 | 0 | [6 empty] | 256989.0000
95 | 15712 | INTERNAL PLASTER WORK 1ST FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3874 | 1ST FLOOR SLAB | [5 empty] | 256989.0000
96 | 15713 | INTERNAL PLASTER WORK 2ND FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3875 | 2ND FLOOR SLAB | [5 empty] | 256989.0000
97 | 15714 | INTERNAL PLASTER WORK 3RD FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3875 | 2ND FLOOR SLAB | [5 empty] | 256989.0000
98 | 15715 | INTERNAL PLASTER WORK 4TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3875 | 2ND FLOOR SLAB | [5 empty] | 256989.0000
99 | 15716 | INTERNAL PLASTER WORK 5TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3878 | 5TH FLOOR SLAB | [5 empty] | 256989.0000
100 | 15717 | INTERNAL PLASTER WORK 6TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3879 | 6TH FLOOR SLAB | [5 empty] | 256989.0000
101 | 15718 | INTERNAL PLASTER WORK 7TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
102 | 15719 | INTERNAL PLASTER WORK 8TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
103 | 15720 | INTERNAL PLASTER WORK 9TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
104 | 15721 | INTERNAL PLASTER WORK 10TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
105 | 15722 | INTERNAL PLASTER WORK 11TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
106 | 15723 | INTERNAL PLASTER WORK12TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
107 | 15724 | INTERNAL PLASTER WORK13TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
108 | 15725 | INTERNAL PLASTER WORK 14TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
109 | 15726 | INTERNAL PLASTER WORK 15TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
110 | 15727 | INTERNAL PLASTER WORK 16TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
111 | 15728 | INTERNAL PLASTER WORK 17TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
112 | 15729 | INTERNAL PLASTER WORK 18TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
113 | 15730 | INTERNAL PLASTER WORK 19TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
114 | 15731 | INTERNAL PLASTER WORK 20TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
115 | 15732 | INTERNAL PLASTER WORK 21ST FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
116 | 15733 | INTERNAL PLASTER WORK 22ND FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
117 | 15734 | INTERNAL PLASTER WORK 23RD FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
118 | 15735 | INTERNAL PLASTER WORK 24TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
119 | 15736 | GROUND FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3880 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
120 | 15737 | INTERNAL PLASTER TERRACE FLOOR WORK | SQF | 131633.0000 | 131633.0000 | 94 | 15710 | 4 | 3881 | TERRACE FLOOR WORK | [5 empty] | 256989.0000
121 | 15711 | EXTERNAL PLASTER WORK |  | 0.0000 | 0.0000 | 93 | 15606 | 31 | 0 | [6 empty] | 256989.0000
122 | 15738 | FRONT SIDE ELEVATION | SQF | 131633.0000 | 131633.0000 | 121 | 15711 | 4 | 3867 | FRONT SIDE ELEVATION | [5 empty] | 256989.0000
123 | 15739 | BACK SIDE ELEVATION | SQF | 131633.0000 | 131633.0000 | 121 | 15711 | 4 | 3868 | BACK SIDE ELEVATION | [5 empty] | 256989.0000
124 | 15740 | RIGHT SIDE ELEVATION | SQF | 131633.0000 | 131633.0000 | 121 | 15711 | 4 | 3869 | RIGHT SIDE ELEVATION | [5 empty] | 256989.0000
125 | 15741 | LEFT SIDE ELEVATION | SQF | 131633.0000 | 131633.0000 | 121 | 15711 | 4 | 3870 | LEFT SIDE ELEVATION | [5 empty] | 256989.0000
126 | 15607 | FLOORING AND TILING WORK |  | 0.0000 | 0.0000 | 37 | 15601 | 31 | 0 |  | Wing |  |  |  |  | 256989.0000
127 | 15742 | 1ST FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3919 | 1ST FLOOR SLAB | [5 empty] | 256989.0000
128 | 15743 | 2ND FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3920 | 2ND FLOOR SLAB | [5 empty] | 256989.0000
129 | 15744 | 3RD FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3921 | 3RD FLOOR SLAB | [5 empty] | 256989.0000
130 | 15745 | 4TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3922 | 4TH FLOOR SLAB | [5 empty] | 256989.0000
131 | 15746 | 5TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3923 | 5TH FLOOR SLAB | [5 empty] | 256989.0000
132 | 15747 | 6TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3924 | 6TH FLOOR SLAB | [5 empty] | 256989.0000
133 | 15748 | 7TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
134 | 15749 | 8TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
135 | 15750 | 9TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
136 | 15751 | 10TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
137 | 15752 | 11TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
138 | 15753 | 12TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
139 | 15754 | 13TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
140 | 15755 | 14TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
141 | 15756 | 15TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
142 | 15757 | 16TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
143 | 15758 | 17TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
144 | 15759 | 18TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
145 | 15760 | 19TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
146 | 15761 | 20TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
147 | 15762 | 21ST FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
148 | 15763 | 22ND FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
149 | 15764 | 23RD FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
150 | 15765 | 24TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 126 | 15607 | 4 | 3925 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
151 | 15608 | INTERNAL PAINTING WORK |  | 0.0000 | 0.0000 | 37 | 15601 | 31 | 0 | [6 empty] | 256989.0000
152 | 15766 | INTERNAL PAINTING WORK 1ST FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3857 | 1ST FLOOR SLAB | [5 empty] | 256989.0000
153 | 15767 | INTERNAL PAINTING WORK 2ND FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3858 | 2ND FLOOR SLAB | [5 empty] | 256989.0000
154 | 15768 | INTERNAL PAINTING WORK 3RD FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3859 | 3RD FLOOR SLAB | [5 empty] | 256989.0000
155 | 15769 | INTERNAL PAINTING WORK 4TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3860 | 4TH FLOOR SLAB | [5 empty] | 256989.0000
156 | 15770 | INTERNAL PAINTING WORK 5TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3861 | 5TH FLOOR SLAB | [5 empty] | 256989.0000
157 | 15771 | INTERNAL PAINTING WORK 6TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3862 | 6TH FLOOR SLAB | [5 empty] | 256989.0000
158 | 15772 | INTERNAL PAINTING WORK 7TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
159 | 15773 | INTERNAL PAINTING WORK 8TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
160 | 15774 | INTERNAL PAINTING WORK 9TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
161 | 15775 | INTERNAL PAINTING WORK 10TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
162 | 15776 | INTERNAL PAINTING WORK 11TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
163 | 15777 | INTERNAL PAINTING WORK 12TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
164 | 15778 | INTERNAL PAINTING WORK 13TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
165 | 15779 | INTERNAL PAINTING WORK 14TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
166 | 15780 | INTERNAL PAINTING WORK 15TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
167 | 15781 | INTERNAL PAINTING WORK 16TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
168 | 15782 | INTERNAL PAINTING WORK 17TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
169 | 15783 | INTERNAL PAINTING WORK 18TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
170 | 15784 | INTERNAL PAINTING WORK 19TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
171 | 15785 | INTERNAL PAINTING WORK 20TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
172 | 15786 | INTERNAL PAINTING WORK 21ST FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
173 | 15787 | INTERNAL PAINTING WORK 22ND FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
174 | 15788 | INTERNAL PAINTING WORK 23RD FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
175 | 15789 | INTERNAL PAINTING WORK 24TH FLOOR SLAB | SQF | 131633.0000 | 131633.0000 | 151 | 15608 | 4 | 3863 | 7TH FLOOR SLAB | [5 empty] | 256989.0000
176 | 15609 | DOOR AND FITTINGS WORKS |  | 0.0000 | 0.0000 | 37 | 15601 | 31 | 0 | [6 empty] | 256989.0000
177 | 15610 | COMMON AMENITIES |  | 0.0000 | 0.0000 | 37 | 15601 | 31 | 0 |  | Wing |  |  |  |  | 256989.0000
178 | 15611 | SOFFIT CEILING & EXTERNAL FINS |  | 0.0000 | 0.0000 | 37 | 15601 | 31 | 0 |  | Wing |  |  |  |  | 256989.0000
179 | 15612 | ELECTRICAL WORK |  | 0.0000 | 0.0000 | 37 | 15601 | 31 | 0 | [6 empty] | 256989.0000
180 | 15613 | PLUMBING WORK |  | 0.0000 | 0.0000 | 37 | 15601 | 31 | 0 |  | Wing |  |  |  |  | 256989.0000
181 | 15616 | FIRE FIGHTING SYSTEM |  | 0.0000 | 0.0000 | 37 | 15601 | 31 | 0 | [6 empty] | 256989.0000
182 | 15614 | MISC. WORK |  | 0.0000 | 0.0000 | 1 | 15597 | 31 | 0 | [6 empty] | 256989.0000
183 | 15615 | LIFT WORK |  | 0.0000 | 0.0000 | 182 | 15614 | 31 | 0 | [6 empty] | 256989.0000
184 | 15617 | STP WORK |  | 0.0000 | 0.0000 | 182 | 15614 | 31 | 0 | [6 empty] | 256989.0000
185 | 15618 | CCTV, VDP & D2H |  | 0.0000 | 0.0000 | 182 | 15614 | 31 | 0 | [6 empty] | 256989.0000
186 | 15619 | MECHANICAL PARKING |  | 0.0000 | 0.0000 | 182 | 15614 | 31 | 0 | [6 empty] | 256989.0000
187 | 15620 | DG SET |  | 0.0000 | 0.0000 | 182 | 15614 | 31 | 0 | [6 empty] | 256989.0000
188 | 15621 | TRANSFORMER ROOM WORK |  | 0.0000 | 0.0000 | 182 | 15614 | 31 | 0 | [6 empty] | 256989.0000
189 | 15622 | PUMPS |  | 0.0000 | 0.0000 | 182 | 15614 | 31 | 0 | [6 empty] | 256989.0000